## Project Plan
Tasks | Owner | Status | Due Date
Create Project 1 Group 5 repo | Shay | Done
Combine the Fast Food data sheets | Shay | In Progress | 2021-10-09
Combine the Diabetes prevalence and population data for each year | Matt | Done | 2021-10-07
Add FIPS numbers to fast food data | Hai | Pending | 2021-10-08
Clean / validate Fast Food Data | Mat | Pending | 2021-10-09
Clean / validate Diabetes Data | Shirine | Pending | 2021-10-09
combine diabetes and fast food data
bar chart diabetes % by county (top 10-20 counties)
line plots by year (x-axis = year; y-axis = diabetes prevalence)
scatter plots population vs diabetes
bar chart fast food restaurants by county (top 10-20 counties)
Scatter plot by year (x-axis = year; y-axis = fast food restaurants/county)
hypothesis test |  |  | 2021-10-11
Final Merge and test |  |  | 2021-10-12

## Timeline
2021-10-02
2021-10-03
2021-10-04 | Proposal approval
2021-10-05 | Create new Repo "project-1-group-5"
2021-10-06
2021-10-07 | Data Sets Combined - Notebooks merged to main branch | Hypothesis Test Lesson
2021-10-08
2021-10-09 | Clean Up Completed
2021-10-10 | Data Sets Merged
2021-10-11 | Analysis
2021-10-12 | Project Completion
2021-10-13
2021-10-14 | Project Submission